## Atomic Task Tracker
PPRS Atomic Task Tracker — Deadline 5 November 2026
Task ID | Planned Date | Week | Major Deliverable | Workstream | Atomic Task | Evidence / Deliverable | Planned Hours | Priority | Dependency | Milestone | Status | Completion % | Actual Completion Date | Evidence / Link | Quality /5 | Rework Required? | Remarks
T001 | 2026-09-20 | Start | 4. Proof of Concept | Dataset | List the exact market/liquidity/report datasets already identified and unresolved data risks | Dataset readiness checklist | 1 | High |  |  | Not Started | 0
T002 | 2026-09-20 | Start | 1. Literature Review | Literature Review | Review current literature/gap matrix and mark every unsupported absolute claim | Absolute-claim issue list | 1 | High |  |  | Not Started | 0
T003 | 2026-09-20 | Start | Supporting / QA | Project Control | Create the PPRS work tracker and evidence folders | Tracker + evidence folders | 0.5 | High |  |  | Not Started | 0
T004 | 2026-09-20 | Start | Supporting / QA | Project Control | Review all supervision feedback from the previous discussion and extract required corrections | Supervisor-action checklist | 1.5 | High |  |  | Not Started | 0
T005 | 2026-09-20 | Start | 3. PPRS Handout | Research Design | Draft the technical contribution to Body of Knowledge in one paragraph | Technical contribution v0.8 | 1 | High |  |  | Not Started | 0
T006 | 2026-09-20 | Start | 3. PPRS Handout | Research Design | Freeze sentiment as non-core / removed from the core research scope | Scope decision record | 0.5 | High |  |  | Not Started | 0
T007 | 2026-09-20 | Start | 3. PPRS Handout | Research Design | Rewrite one main gap and maximum two sub-gaps in provisional form | Gap set v0.9 | 1.5 | High |  |  | Not Started | 0
T008 | 2026-09-20 | Start | 3. PPRS Handout | Research Design | Write explicit Task–Domain–Constraints statement | Task–Domain–Constraints v1.0 | 1 | High |  |  | Not Started | 0
T009 | 2026-09-21 | W1 | 1. Literature Review | Literature Review | Add the missing 2025–2026 CSE papers already identified to the Literature Survey Matrix | Updated rows for missing CSE papers | 1 | High |  |  | Not Started | 0
T010 | 2026-09-21 | W1 | 3. PPRS Handout | PPRS Handout | Create the 15-page handout skeleton with all required headings | Handout v0.1 structure | 0.75 | High |  |  | Not Started | 0
T011 | 2026-09-21 | W1 | 4. Proof of Concept | PoC | Create the PoC repository and folder structure | Version-controlled PoC repository | 0.5 | High |  |  | Not Started | 0
T012 | 2026-09-21 | W1 | 2. Requirement Elicitation | Requirement Elicitation | Create the requirement-source list: literature, dataset constraints, supervisor feedback, technical feasibility | Requirement source register | 0.75 | High |  |  | Not Started | 0
T013 | 2026-09-22 | W1 | 1. Literature Review | Literature Review | Read one missing CSE 2025–2026 paper in full and complete one matrix row | 1 completed literature row | 1.25 | High |  |  | Not Started | 0
T014 | 2026-09-22 | W1 | 3. PPRS Handout | PPRS Handout | Draft the Problem Background subsection | Problem Background draft | 0.75 | High |  |  | Not Started | 0
T015 | 2026-09-22 | W1 | 4. Proof of Concept | PoC | Test access to one CSE historical market-data source and save a sample | Sample OHLCV file | 0.25 | High |  |  | Not Started | 0
T016 | 2026-09-22 | W1 | 2. Requirement Elicitation | Requirement Elicitation | Extract functional requirements from the refined research gap and proposed methodology | Draft functional requirements | 0.75 | High |  |  | Not Started | 0
T017 | 2026-09-23 | W1 | 1. Literature Review | Literature Review | Read one high-impact multi-agent finance paper and complete one matrix row | 1 completed literature row | 1.25 | High |  |  | Not Started | 0
T018 | 2026-09-23 | W1 | 3. PPRS Handout | PPRS Handout | Draft the Research Problem subsection | Research Problem draft | 0.75 | High |  |  | Not Started | 0
T019 | 2026-09-23 | W1 | 4. Proof of Concept | PoC | Inspect OHLCV sample fields, date range and missing values | Data inspection note | 0.25 | High |  |  | Not Started | 0
T020 | 2026-09-23 | W1 | 2. Requirement Elicitation | Requirement Elicitation | Extract non-functional requirements: reproducibility, modularity, traceability, data integrity, performance | Draft non-functional requirements | 0.75 | High |  |  | Not Started | 0
T021 | 2026-09-24 | W1 | 1. Literature Review | Literature Review | Read one liquidity/execution-friction paper and complete one matrix row | 1 completed literature row | 1.25 | High |  |  | Not Started | 0
T022 | 2026-09-24 | W1 | 3. PPRS Handout | PPRS Handout | Draft the Task–Domain–Constraints subsection | Task–Domain–Constraints draft | 0.5 | High |  |  | Not Started | 0
T023 | 2026-09-24 | W1 | 4. Proof of Concept | PoC | Implement market-data loader for one security | Working data loader | 0.5 | High |  |  | Not Started | 0
T024 | 2026-09-24 | W1 | 2. Requirement Elicitation | Requirement Elicitation | Create requirement IDs and acceptance criteria for each functional requirement | Functional requirements table | 0.75 | High |  |  | Not Started | 0
T025 | 2026-09-25 | W1 | 1. Literature Review | Literature Review | Read one volatility-memory/regime paper and complete one matrix row | 1 completed literature row | 1.25 | High |  |  | Not Started | 0
T026 | 2026-09-25 | W1 | 3. PPRS Handout | PPRS Handout | Draft the provisional Research Gap subsection | Research Gap draft | 0.5 | High |  |  | Not Started | 0
T027 | 2026-09-25 | W1 | 4. Proof of Concept | PoC | Implement basic return calculation from OHLCV | Return feature output | 0.5 | High |  |  | Not Started | 0
T028 | 2026-09-25 | W1 | 2. Requirement Elicitation | Requirement Elicitation | Create requirement IDs and acceptance criteria for each non-functional requirement | Non-functional requirements table | 0.75 | High |  |  | Not Started | 0
T029 | 2026-09-26 | W1 | 1. Literature Review | Literature Review | Consolidate duplicate/overlapping literature findings into thematic notes | Thematic synthesis notes | 1.5 | High |  |  | Not Started | 0
T030 | 2026-09-26 | W1 | 3. PPRS Handout | PPRS Handout | Draft the provisional Aim, RQs and Objectives section | Aim/RQs/Objectives v0.1 | 0.75 | High |  |  | Not Started | 0
T031 | 2026-09-26 | W1 | 4. Proof of Concept | PoC | Implement rolling volatility feature | Rolling volatility output | 1 | High |  |  | Not Started | 0
T032 | 2026-09-26 | W1 | 2. Requirement Elicitation | Requirement Elicitation | Prioritise requirements using Must/Should/Could | Prioritised requirements list | 0.75 | High |  |  | Not Started | 0
T033 | 2026-09-27 | W1 | 1. Literature Review | Literature Review | Write thematic synthesis for liquidity/execution friction | Theme synthesis: liquidity/friction | 1.5 | High |  |  | Not Started | 0
T034 | 2026-09-27 | W1 | 1. Literature Review | Literature Review | Write thematic synthesis for multi-agent financial systems | Theme synthesis: multi-agent finance | 1.5 | High |  |  | Not Started | 0
T035 | 2026-09-27 | W1 | 3. PPRS Handout | PPRS Handout | Integrate Week 1 research-problem, gap, aim, RQ and objective drafts into handout | Handout v0.2 | 1.5 | High |  |  | Not Started | 0
T036 | 2026-09-27 | W1 | 4. Proof of Concept | PoC | Implement turnover/relative-volume liquidity features from available sample | Liquidity feature output | 1.5 | High |  |  | Not Started | 0
T037 | 2026-09-27 | W1 | Supporting / QA | Project Control | Run Week 1 quality audit against the 4.5/5 threshold | Week 1 audit | 1 | High |  |  | Not Started | 0
T038 | 2026-09-27 | W1 | 2. Requirement Elicitation | Requirement Elicitation | Review all elicited requirements against the main gap; remove application-only requirements | Clean requirement set | 1 | High |  |  | Not Started | 0
T039 | 2026-09-28 | W2 | 1. Literature Review | Literature Review | Write thematic synthesis for volatility memory and regimes | Theme synthesis: volatility | 1 | High |  |  | Not Started | 0
T040 | 2026-09-28 | W2 | 3. PPRS Handout | PPRS Handout | Draft Introduction opening and research motivation | Introduction v0.1 | 0.75 | High |  |  | Not Started | 0
T041 | 2026-09-28 | W2 | 4. Proof of Concept | PoC | Implement Amihud-style illiquidity proxy where trading value is available | Illiquidity feature output | 0.5 | High |  |  | Not Started | 0
T042 | 2026-09-28 | W2 | 2. Requirement Elicitation | Requirement Elicitation | Map every requirement to a research objective or experimental need | Requirement traceability matrix | 0.75 | High |  |  | Not Started | 0
T043 | 2026-09-29 | W2 | 1. Literature Review | Literature Review | Read one high-impact state-aware orchestration paper and complete one matrix row | 1 completed literature row | 1 | High |  |  | Not Started | 0
T044 | 2026-09-29 | W2 | 3. PPRS Handout | PPRS Handout | Draft Literature Review theme 1: multi-agent orchestration | LR theme 1 draft | 0.75 | High |  |  | Not Started | 0
T045 | 2026-09-29 | W2 | 4. Proof of Concept | PoC | Create market-state feature table for one security | Market-state table | 0.5 | High |  |  | Not Started | 0
T046 | 2026-09-29 | W2 | 2. Requirement Elicitation | Requirement Elicitation | Define data requirements for market, liquidity, volatility and reports | Data requirements specification | 0.75 | High |  |  | Not Started | 0
T047 | 2026-09-30 | W2 | 1. Literature Review | Literature Review | Read one high-impact execution/market-impact paper and complete one matrix row | 1 completed literature row | 1 | High |  |  | Not Started | 0
T048 | 2026-09-30 | W2 | 3. PPRS Handout | PPRS Handout | Draft Literature Review theme 2: liquidity and execution friction | LR theme 2 draft | 0.75 | High |  |  | Not Started | 0
T049 | 2026-09-30 | W2 | 4. Proof of Concept | PoC | Create baseline static equal-weight agent combiner | Static combiner prototype | 0.5 | High |  |  | Not Started | 0
T050 | 2026-09-30 | W2 | 2. Requirement Elicitation | Requirement Elicitation | Define interface requirements between agents and orchestrator | Agent interface requirements | 0.75 | High |  |  | Not Started | 0
T051 | 2026-10-01 | W2 | 1. Literature Review | Literature Review | Read one high-impact volatility/regime paper and complete one matrix row | 1 completed literature row | 1 | High |  |  | Not Started | 0
T052 | 2026-10-01 | W2 | 3. PPRS Handout | PPRS Handout | Draft Literature Review theme 3: volatility persistence/regimes | LR theme 3 draft | 0.75 | High |  |  | Not Started | 0
T053 | 2026-10-01 | W2 | 4. Proof of Concept | PoC | Create placeholder agent-output schema with signal, confidence and evidence fields | Agent-output schema | 0.5 | High |  |  | Not Started | 0
T054 | 2026-10-01 | W2 | 2. Requirement Elicitation | Requirement Elicitation | Define evaluation requirements: baselines, ablations, metrics, significance tests | Evaluation requirements | 0.75 | High |  |  | Not Started | 0
T055 | 2026-10-02 | W2 | 1. Literature Review | Literature Review | Re-check all novelty statements against the strongest papers read so far | Novelty challenge notes | 1 | High |  |  | Not Started | 0
T056 | 2026-10-02 | W2 | 3. PPRS Handout | PPRS Handout | Draft Literature Review theme 4: CSE/frontier-market evidence | LR theme 4 draft | 0.75 | High |  |  | Not Started | 0
T057 | 2026-10-02 | W2 | 4. Proof of Concept | PoC | Implement basic technical-agent signal from a minimal justified feature set | Technical-agent output | 0.5 | High |  |  | Not Started | 0
T058 | 2026-10-02 | W2 | 2. Requirement Elicitation | Requirement Elicitation | Define reproducibility requirements: seeds, versioning, data lineage, experiment logs | Reproducibility requirements | 0.75 | High |  |  | Not Started | 0
T059 | 2026-10-03 | W2 | 1. Literature Review | Literature Review | Complete literature-gap synthesis table: known, limitation, unresolved issue, proposed response | Literature-gap synthesis table | 1 | High |  |  | Not Started | 0
T060 | 2026-10-03 | W2 | 3. PPRS Handout | PPRS Handout | Draft Dataset Strategy subsection | Dataset Strategy draft | 0.75 | High |  |  | Not Started | 0
T061 | 2026-10-03 | W2 | 4. Proof of Concept | PoC | Implement liquidity-agent output with a continuous liquidity score | Liquidity-agent output | 1.5 | High |  |  | Not Started | 0
T062 | 2026-10-03 | W2 | 2. Requirement Elicitation | Requirement Elicitation | Freeze Requirement Specification v1.0 | Requirements v1.0 | 0.75 | High |  | Requirements v1.0 | Not Started | 0
T063 | 2026-10-04 | W2 | 1. Literature Review | Literature Review | Complete a full quality review of the Literature Survey Matrix; fill missing fields | Literature Matrix cleaned | 1.5 | High |  | LR matrix substantially complete | Not Started | 0
T064 | 2026-10-04 | W2 | 3. PPRS Handout | PPRS Handout | Integrate all Literature Review themes into one coherent section | Literature Review v0.8 | 2 | High |  |  | Not Started | 0
T065 | 2026-10-04 | W2 | 4. Proof of Concept | PoC | Implement volatility-agent baseline using rolling volatility and GARCH if stable | Volatility-agent baseline | 2 | High |  |  | Not Started | 0
T066 | 2026-10-04 | W2 | 4. Proof of Concept | PoC | Load a small set of CSE annual reports and verify PDF text extraction | Report corpus sample | 1 | High |  |  | Not Started | 0
T067 | 2026-10-04 | W2 | Supporting / QA | Project Control | Run Week 2 quality audit and list all tasks below 4.5/5 readiness | Week 2 audit | 1.5 | High |  |  | Not Started | 0
T068 | 2026-10-05 | W3 | 1. Literature Review | Literature Review | Read one paper most likely to invalidate the proposed main gap | Adversarial literature row | 1 | High |  |  | Not Started | 0
T069 | 2026-10-05 | W3 | 3. PPRS Handout | Methodology | Draft research-design overview: comparative experimental study using secondary data | Methodology overview v0.1 | 0.5 | High |  |  | Not Started | 0
T070 | 2026-10-05 | W3 | 3. PPRS Handout | PPRS Handout | Revise Research Gap section after adversarial literature check | Research Gap v0.8 | 0.75 | High |  |  | Not Started | 0
T071 | 2026-10-05 | W3 | 4. Proof of Concept | PoC | Implement simple report retrieval over the sample PDF corpus | Fundamental retrieval prototype | 0.75 | High |  |  | Not Started | 0
T072 | 2026-10-06 | W3 | 1. Literature Review | Literature Review | Finalise main-gap evidence citations from multiple papers | Gap evidence set | 0.75 | High |  |  | Not Started | 0
T073 | 2026-10-06 | W3 | 3. PPRS Handout | Methodology | Draft data-acquisition and preprocessing methodology | Data methodology draft | 0.5 | High |  |  | Not Started | 0
T074 | 2026-10-06 | W3 | 3. PPRS Handout | PPRS Handout | Draft Technical Contribution to BoK subsection | Technical contribution draft | 0.75 | High |  |  | Not Started | 0
T075 | 2026-10-06 | W3 | 4. Proof of Concept | PoC | Implement fundamental-agent output with evidence reference and confidence placeholder | Fundamental-agent output | 1 | High |  |  | Not Started | 0
T076 | 2026-10-07 | W3 | 1. Literature Review | Literature Review | Finalise sub-gap 1 evidence: liquidity/execution friction | Sub-gap 1 evidence set | 0.75 | High |  |  | Not Started | 0
T077 | 2026-10-07 | W3 | 3. PPRS Handout | Methodology | Draft baseline-comparison methodology | Baseline methodology draft | 0.75 | High |  |  | Not Started | 0
T078 | 2026-10-07 | W3 | 3. PPRS Handout | PPRS Handout | Draft Sub-gap 1 subsection | Sub-gap 1 draft | 0.5 | High |  |  | Not Started | 0
T079 | 2026-10-07 | W3 | 4. Proof of Concept | PoC | Create unified agent-output table for technical, liquidity, volatility and fundamental agents | Unified agent-output table | 1 | High |  |  | Not Started | 0
T080 | 2026-10-08 | W3 | 1. Literature Review | Literature Review | Finalise sub-gap 2 evidence: volatility persistence and risk control | Sub-gap 2 evidence set | 0.75 | High |  |  | Not Started | 0
T081 | 2026-10-08 | W3 | 3. PPRS Handout | Methodology | Draft ablation-study methodology | Ablation methodology draft | 0.75 | High |  |  | Not Started | 0
T082 | 2026-10-08 | W3 | 3. PPRS Handout | PPRS Handout | Draft Sub-gap 2 subsection | Sub-gap 2 draft | 0.5 | High |  |  | Not Started | 0
T083 | 2026-10-08 | W3 | 4. Proof of Concept | PoC | Implement static equal-weight orchestration over unified agent outputs | Static orchestration output | 1 | High |  |  | Not Started | 0
T084 | 2026-10-09 | W3 | 1. Literature Review | Literature Review | Close remaining unread or incomplete literature rows needed for the gap | No critical LR row left incomplete | 0.75 | High |  |  | Not Started | 0
T085 | 2026-10-09 | W3 | 3. PPRS Handout | Methodology | Draft evaluation metrics section | Evaluation metrics draft | 0.5 | High |  |  | Not Started | 0
T086 | 2026-10-09 | W3 | 3. PPRS Handout | PPRS Handout | Revise Aim, Research Questions and Objectives for exact alignment with gap | Aim/RQs/Objectives v0.9 | 0.75 | High |  |  | Not Started | 0
T087 | 2026-10-09 | W3 | 4. Proof of Concept | PoC | Define initial adaptive-weighting rule using liquidity, volatility/persistence and agent confidence | Adaptive-weighting rule v0.1 | 1 | High |  |  | Not Started | 0
T088 | 2026-10-10 | W3 | 1. Literature Review | Literature Review | Prepare final thematic literature synthesis notes for writing | Final LR synthesis notes | 0.75 | High |  |  | Not Started | 0
T089 | 2026-10-10 | W3 | 3. PPRS Handout | Methodology | Draft experimental split / walk-forward strategy | Experimental split draft | 0.5 | High |  |  | Not Started | 0
T090 | 2026-10-10 | W3 | 3. PPRS Handout | PPRS Handout | Rewrite Literature Review as synthesis, removing paper-by-paper narration | Literature Review v0.9 | 1.25 | High |  |  | Not Started | 0
T091 | 2026-10-10 | W3 | 4. Proof of Concept | PoC | Implement adaptive orchestrator v0.1 | Adaptive orchestrator v0.1 | 1.5 | High |  |  | Not Started | 0
T092 | 2026-10-11 | W3 | 3. PPRS Handout | Methodology | Draft risks, assumptions and limitations | Methodology limitations draft | 1 | High |  |  | Not Started | 0
T093 | 2026-10-11 | W3 | 3. PPRS Handout | PPRS Handout | Complete first integrated draft of Introduction + Problem + Literature + Gap | Handout front half v1.0 | 2 | High |  |  | Not Started | 0
T094 | 2026-10-11 | W3 | 4. Proof of Concept | PoC | Run one ablation removing liquidity conditioning | Ablation result: -liquidity | 1 | High |  |  | Not Started | 0
T095 | 2026-10-11 | W3 | 4. Proof of Concept | PoC | Run static vs adaptive orchestration on a small sample | Preliminary comparison results | 2 | High |  |  | Not Started | 0
T096 | 2026-10-11 | W3 | Supporting / QA | Project Control | Run Week 3 review and freeze the core research scope | Scope freeze record | 2 | High |  | Core scope frozen | Not Started | 0
T097 | 2026-10-12 | W4 | 3. PPRS Handout | Methodology | Formalise the adaptive orchestration function and variables mathematically | Formal orchestration definition | 1 | High |  |  | Not Started | 0
T098 | 2026-10-12 | W4 | 3. PPRS Handout | PPRS Handout | Insert formal orchestration definition into methodology | Methodology formula section | 0.75 | High |  |  | Not Started | 0
T099 | 2026-10-12 | W4 | 4. Proof of Concept | PoC | Refactor orchestrator to match the formal definition | Adaptive orchestrator v0.2 | 1 | High |  |  | Not Started | 0
T100 | 2026-10-12 | W4 | 2. Requirement Elicitation | Requirement Elicitation | Verify PoC design satisfies all Must requirements | Requirements verification note | 0.25 | High |  |  | Not Started | 0
T101 | 2026-10-13 | W4 | 3. PPRS Handout | Methodology | Define agent-confidence calculation or calibration method | Confidence methodology | 0.75 | High |  |  | Not Started | 0
T102 | 2026-10-13 | W4 | 3. PPRS Handout | PPRS Handout | Draft agent architecture subsection | Agent architecture draft | 0.75 | High |  |  | Not Started | 0
T103 | 2026-10-13 | W4 | 4. Proof of Concept | PoC | Implement agent-confidence field consistently across agents | Confidence-enabled outputs | 1 | High |  |  | Not Started | 0
T104 | 2026-10-13 | W4 | 2. Requirement Elicitation | Requirement Elicitation | Update traceability matrix with implemented PoC evidence | Traceability matrix updated | 0.5 | High |  |  | Not Started | 0
T105 | 2026-10-14 | W4 | 3. PPRS Handout | Methodology | Define liquidity-state construction and thresholds/proxy method | Liquidity-state methodology | 0.75 | High |  |  | Not Started | 0
T106 | 2026-10-14 | W4 | 3. PPRS Handout | PPRS Handout | Draft liquidity-friction methodology subsection | Liquidity methodology draft | 0.75 | High |  |  | Not Started | 0
T107 | 2026-10-14 | W4 | 4. Proof of Concept | PoC | Implement friction-aware evaluation layer using available liquidity proxies | Friction-aware evaluator | 1 | High |  |  | Not Started | 0
T108 | 2026-10-14 | W4 | 2. Requirement Elicitation | Requirement Elicitation | Verify liquidity-related requirements and acceptance criteria | Liquidity requirement verification | 0.5 | High |  |  | Not Started | 0
T109 | 2026-10-15 | W4 | 3. PPRS Handout | Methodology | Define volatility/persistence-state construction | Volatility-state methodology | 0.75 | High |  |  | Not Started | 0
T110 | 2026-10-15 | W4 | 3. PPRS Handout | PPRS Handout | Draft volatility/persistence methodology subsection | Volatility methodology draft | 0.75 | High |  |  | Not Started | 0
T111 | 2026-10-15 | W4 | 4. Proof of Concept | PoC | Implement persistence or regime input in simplified form | Persistence/regime feature | 1 | High |  |  | Not Started | 0
T112 | 2026-10-15 | W4 | 2. Requirement Elicitation | Requirement Elicitation | Verify volatility-related requirements and acceptance criteria | Volatility requirement verification | 0.5 | High |  |  | Not Started | 0
T113 | 2026-10-16 | W4 | 3. PPRS Handout | Methodology | Freeze baseline definitions and comparison protocol | Baseline protocol v1.0 | 0.75 | High |  |  | Not Started | 0
T114 | 2026-10-16 | W4 | 3. PPRS Handout | PPRS Handout | Draft baseline and ablation subsection | Baseline/ablation draft | 0.75 | High |  |  | Not Started | 0
T115 | 2026-10-16 | W4 | 4. Proof of Concept | PoC | Run static, adaptive and one simplified state-aware baseline on same sample | Three-baseline result set | 1 | High |  |  | Not Started | 0
T116 | 2026-10-16 | W4 | 2. Requirement Elicitation | Requirement Elicitation | Verify evaluation-related requirements | Evaluation requirement verification | 0.5 | High |  |  | Not Started | 0
T117 | 2026-10-17 | W4 | 3. PPRS Handout | Methodology | Freeze ablation list and experiment naming convention | Ablation protocol v1.0 | 0.75 | High |  |  | Not Started | 0
T118 | 2026-10-17 | W4 | 3. PPRS Handout | PPRS Handout | Draft Requirement Specification section | Requirements section draft | 0.75 | High |  |  | Not Started | 0
T119 | 2026-10-17 | W4 | 4. Proof of Concept | PoC | Run ablation removing confidence conditioning | Ablation result: -confidence | 1.25 | High |  |  | Not Started | 0
T120 | 2026-10-17 | W4 | 4. Proof of Concept | PoC | Run ablation removing volatility/persistence conditioning | Ablation result: -volatility | 1.25 | High |  |  | Not Started | 0
T121 | 2026-10-18 | W4 | 3. PPRS Handout | Methodology | Complete Methodology v0.8 | Methodology v0.8 | 1.5 | High |  |  | Not Started | 0
T122 | 2026-10-18 | W4 | 3. PPRS Handout | PPRS Handout | Create final implementation-pipeline diagram | Implementation pipeline diagram | 1.5 | High |  | Pipeline frozen | Not Started | 0
T123 | 2026-10-18 | W4 | 3. PPRS Handout | PPRS Handout | Create final research-architecture diagram | Architecture diagram | 1.5 | High |  |  | Not Started | 0
T124 | 2026-10-18 | W4 | 4. Proof of Concept | PoC | Document PoC inputs, outputs and preliminary results | PoC evidence pack v0.8 | 2 | High |  |  | Not Started | 0
T125 | 2026-10-18 | W4 | Supporting / QA | Project Control | Run Week 4 audit; prohibit new scope after today | Scope-lock audit | 1.5 | High |  | No new scope | Not Started | 0
T126 | 2026-10-19 | W5 | 1. Literature Review | Literature Review | Perform citation completeness check on Introduction and Problem Background | Citation check | 0.5 | High |  |  | Not Started | 0
T127 | 2026-10-19 | W5 | 3. PPRS Handout | PPRS Handout | Write final Introduction section | Introduction v1.0 | 1 | High |  |  | Not Started | 0
T128 | 2026-10-19 | W5 | 3. PPRS Handout | PPRS Handout | Write final Problem Background section | Problem Background v1.0 | 1 | High |  |  | Not Started | 0
T129 | 2026-10-19 | W5 | 4. Proof of Concept | PoC | Fix any blocking PoC defect discovered during Week 4 audit | PoC defect fix | 0.5 | High |  |  | Not Started | 0
T130 | 2026-10-20 | W5 | 1. Literature Review | Literature Review | Verify every major gap claim has at least two supporting sources where possible | Gap citation verification | 0.75 | High |  |  | Not Started | 0
T131 | 2026-10-20 | W5 | 3. PPRS Handout | PPRS Handout | Finalise Literature Review section | Literature Review v1.0 | 1.5 | High |  |  | Not Started | 0
T132 | 2026-10-20 | W5 | 4. Proof of Concept | PoC | Prepare one clean reproducible PoC run script/notebook | Reproducible PoC run | 0.75 | High |  |  | Not Started | 0
T133 | 2026-10-21 | W5 | 3. PPRS Handout | Methodology | Check one-to-one mapping between RQs and experiments | RQ-experiment mapping | 0.5 | High |  |  | Not Started | 0
T134 | 2026-10-21 | W5 | 3. PPRS Handout | PPRS Handout | Finalise Aim, RQs and Objectives | Aim/RQs/Objectives v1.0 | 0.75 | High |  |  | Not Started | 0
T135 | 2026-10-21 | W5 | 3. PPRS Handout | PPRS Handout | Finalise Research Gap and Technical Contribution section | Gap/Contribution v1.0 | 1 | High |  |  | Not Started | 0
T136 | 2026-10-21 | W5 | 4. Proof of Concept | PoC | Capture final PoC outputs/screenshots/tables for handout | PoC evidence images/tables | 0.75 | High |  |  | Not Started | 0
T137 | 2026-10-22 | W5 | 3. PPRS Handout | PPRS Handout | Finalise Dataset Strategy subsection | Dataset Strategy v1.0 | 0.5 | High |  |  | Not Started | 0
T138 | 2026-10-22 | W5 | 3. PPRS Handout | PPRS Handout | Finalise Methodology section | Methodology v1.0 | 1.25 | High |  |  | Not Started | 0
T139 | 2026-10-22 | W5 | 4. Proof of Concept | PoC | Freeze PoC version used for PPRS evidence | PoC v1.0 tag | 0.5 | High |  | PoC frozen | Not Started | 0
T140 | 2026-10-22 | W5 | 2. Requirement Elicitation | Requirement Elicitation | Freeze Requirement Specification v1.1 with traceability | Requirements v1.1 | 0.75 | High |  |  | Not Started | 0
T141 | 2026-10-23 | W5 | 3. PPRS Handout | PPRS Handout | Draft PoC feasibility/results subsection | PoC subsection draft | 0.75 | High |  |  | Not Started | 0
T142 | 2026-10-23 | W5 | 3. PPRS Handout | PPRS Handout | Finalise Architecture and Implementation Pipeline section | Architecture/Pipeline v1.0 | 0.75 | High |  |  | Not Started | 0
T143 | 2026-10-23 | W5 | 3. PPRS Handout | PPRS Handout | Finalise Requirement Specification section | Requirements section v1.0 | 0.75 | High |  |  | Not Started | 0
T144 | 2026-10-23 | W5 | Supporting / QA | Project Control | Check page-budget against 15-page limit | Page-budget audit | 0.75 | High |  |  | Not Started | 0
T145 | 2026-10-24 | W5 | 3. PPRS Handout | PPRS Handout | Assemble complete 15-page handout Version 1.0 | Complete handout v1.0 | 2 | High |  | Complete handout v1.0 | Not Started | 0
T146 | 2026-10-24 | W5 | 3. PPRS Handout | PPRS Handout | Check figure and table numbering | Figure/table check | 0.5 | High |  |  | Not Started | 0
T147 | 2026-10-24 | W5 | 3. PPRS Handout | PPRS Handout | Check references and DOI/link consistency | Reference check | 0.75 | High |  |  | Not Started | 0
T148 | 2026-10-24 | W5 | Supporting / QA | Project Control | Record all defects found in handout v1.0 | Defect list | 0.75 | High |  |  | Not Started | 0
T149 | 2026-10-25 | W5 | 3. PPRS Handout | PPRS Handout | Ensure gap → contribution → methodology → experiment alignment | Alignment audit | 1 | High |  |  | Not Started | 0
T150 | 2026-10-25 | W5 | 3. PPRS Handout | PPRS Handout | Remove unsupported absolute claims | Absolute-claim cleanup | 0.75 | High |  |  | Not Started | 0
T151 | 2026-10-25 | W5 | 3. PPRS Handout | PPRS Handout | Run full critical review for logical flow and duplication | Handout critical review | 1.5 | High |  |  | Not Started | 0
T152 | 2026-10-25 | W5 | 5. Recorded Video | PPRS Video | Create recorded-presentation slide outline | Video slide outline | 1.25 | High |  |  | Not Started | 0
T153 | 2026-10-25 | W5 | 4. Proof of Concept | PoC | Re-run PoC from clean environment and record reproducibility result | Clean-run evidence | 1 | High |  |  | Not Started | 0
T154 | 2026-10-25 | W5 | Supporting / QA | Project Control | Run Week 5 quality gate; all core deliverables must be >=4.5/5 | Week 5 quality gate | 1.5 | High |  |  | Not Started | 0
T155 | 2026-10-26 | W6 | 3. PPRS Handout | PPRS Handout | Revise handout from Week 5 defect list | Handout v1.1 | 1.25 | High |  |  | Not Started | 0
T156 | 2026-10-26 | W6 | 5. Recorded Video | PPRS Video | Build slides 1–5: problem, background, literature, gap, contribution | Slides 1–5 | 1 | High |  |  | Not Started | 0
T157 | 2026-10-26 | W6 | 4. Proof of Concept | PoC | Create concise PoC demonstration sequence for recording | PoC demo sequence | 0.75 | High |  |  | Not Started | 0
T158 | 2026-10-27 | W6 | 3. PPRS Handout | PPRS Handout | Finalise diagrams and ensure readability at normal zoom | Final diagrams | 0.75 | High |  |  | Not Started | 0
T159 | 2026-10-27 | W6 | 5. Recorded Video | PPRS Video | Build slides 11–15: PoC, evaluation, risks, plan, conclusion | Slides 11–15 | 1 | High |  |  | Not Started | 0
T160 | 2026-10-27 | W6 | 5. Recorded Video | PPRS Video | Build slides 6–10: RQs, data, methodology, architecture, pipeline | Slides 6–10 | 1.25 | High |  |  | Not Started | 0
T161 | 2026-10-28 | W6 | 3. PPRS Handout | PPRS Handout | Complete final language and formatting edit | Handout v1.2 | 1 | High |  |  | Not Started | 0
T162 | 2026-10-28 | W6 | 5. Recorded Video | PPRS Video | Time one full spoken run and record duration | Timing result | 1 | High |  |  | Not Started | 0
T163 | 2026-10-28 | W6 | 5. Recorded Video | PPRS Video | Write speaking notes for each recorded slide | Video script v0.8 | 1 | High |  |  | Not Started | 0
T164 | 2026-10-29 | W6 | 3. PPRS Handout | PPRS Handout | Perform final citation and reference cross-check | Final citation audit | 0.75 | High |  |  | Not Started | 0
T165 | 2026-10-29 | W6 | 5. Recorded Video | PPRS Video | Record draft video | Draft recorded presentation | 1 | High |  |  | Not Started | 0
T166 | 2026-10-29 | W6 | 5. Recorded Video | PPRS Video | Revise script to fit allowed duration | Video script v1.0 | 0.75 | High |  |  | Not Started | 0
T167 | 2026-10-29 | W6 | Supporting / QA | Project Control | Review draft video for technical clarity and missing evidence | Video defect list | 0.5 | High |  |  | Not Started | 0
T168 | 2026-10-30 | W6 | 3. PPRS Handout | PPRS Handout | Freeze content; only critical corrections allowed after today | Handout content freeze | 0.5 | High |  | Handout content frozen | Not Started | 0
T169 | 2026-10-30 | W6 | 5. Recorded Video | PPRS Video | Correct slide defects identified from draft recording | Slides v1.1 | 0.75 | High |  |  | Not Started | 0
T170 | 2026-10-30 | W6 | 5. Recorded Video | PPRS Video | Record second video version | Video v0.9 | 1 | High |  |  | Not Started | 0
T171 | 2026-10-30 | W6 | 5. Recorded Video | PPRS Video | Review audio, timing, slide readability and PoC demo | Video QA result | 0.75 | High |  |  | Not Started | 0
T172 | 2026-10-31 | W6 | 3. PPRS Handout | PPRS Handout | Run independent/self checklist against all required PPRS sections | PPRS compliance checklist | 1 | High |  |  | Not Started | 0
T173 | 2026-10-31 | W6 | 5. Recorded Video | PPRS Video | Apply final presentation corrections | Slides/script final corrections | 1 | High |  |  | Not Started | 0
T174 | 2026-10-31 | W6 | 5. Recorded Video | PPRS Video | Record final candidate video | Final-candidate video | 1.5 | High |  |  | Not Started | 0
T175 | 2026-10-31 | W6 | Supporting / QA | Project Control | Back up handout, slides, video and PoC evidence | Backup confirmation | 0.5 | High |  |  | Not Started | 0
T176 | 2026-11-01 | W6 | 3. PPRS Handout | PPRS Handout | Proofread complete handout from start to finish | Proofread notes | 1.5 | High |  |  | Not Started | 0
T177 | 2026-11-01 | W6 | 3. PPRS Handout | PPRS Handout | Resolve all proofreading issues | Handout vFinal candidate | 1 | High |  |  | Not Started | 0
T178 | 2026-11-01 | W6 | 5. Recorded Video | PPRS Video | Resolve final video defects and export final recording | Final recorded video | 2 | High |  | Recorded video complete | Not Started | 0
T179 | 2026-11-01 | W6 | 5. Recorded Video | PPRS Video | Watch final candidate video end-to-end and log defects | Final video QA log | 1 | High |  |  | Not Started | 0
T180 | 2026-11-01 | W6 | 4. Proof of Concept | PoC | Package PoC evidence and reproducibility instructions | PoC evidence package | 1 | High |  |  | Not Started | 0
T181 | 2026-11-01 | W6 | Supporting / QA | Project Control | Run Week 6 final readiness audit | Final readiness audit | 1.5 | High |  |  | Not Started | 0
T182 | 2026-11-02 | W7 | 3. PPRS Handout | PPRS Handout | Run final page-limit, numbering and formatting check | Submission-ready handout | 1 | High |  |  | Not Started | 0
T183 | 2026-11-02 | W7 | 5. Recorded Video | PPRS Video | Verify final video file opens, plays and has correct duration | Video technical verification | 0.5 | High |  |  | Not Started | 0
T184 | 2026-11-02 | W7 | 4. Proof of Concept | PoC | Verify PoC evidence links/files referenced in handout are accessible | PoC link verification | 0.75 | High |  |  | Not Started | 0
T185 | 2026-11-02 | W7 | Supporting / QA | Project Control | Verify all submission filenames and required artefacts | Submission package checklist | 0.75 | High |  |  | Not Started | 0
T186 | 2026-11-03 | W7 | 3. PPRS Handout | PPRS Handout | Perform final typo-only review; no structural rewrite | Final typo check | 1 | High |  |  | Not Started | 0
T187 | 2026-11-03 | W7 | 5. Recorded Video | PPRS Video | Perform one final content-consistency check against handout | Video-handout consistency check | 0.75 | High |  |  | Not Started | 0
T188 | 2026-11-03 | W7 | Supporting / QA | Project Control | Check submission instructions and deadline details | Deadline compliance check | 0.75 | High |  |  | Not Started | 0
T189 | 2026-11-03 | W7 | Supporting / QA | Project Control | Create submission backup copy in a second location | Backup copy | 0.5 | High |  |  | Not Started | 0
T190 | 2026-11-04 | W7 | 3. PPRS Handout | PPRS Handout | Freeze final handout PDF/export | Final handout | 0.75 | High |  | Handout complete | Not Started | 0
T191 | 2026-11-04 | W7 | 5. Recorded Video | PPRS Video | Freeze final recorded video | Final video | 0.75 | High |  | Video complete | Not Started | 0
T192 | 2026-11-04 | W7 | Supporting / QA | Project Control | Assemble final submission package | Final submission package | 0.75 | High |  |  | Not Started | 0
T193 | 2026-11-04 | W7 | Supporting / QA | Project Control | Run final completeness checklist against all PPRS deliverables | Final completeness checklist | 0.75 | High |  |  | Not Started | 0
T194 | 2026-11-05 | W7 | 6. Live Presentation | Live Presentation | Create post-deadline live-presentation issue list from likely viva questions | Live presentation issue list | 0.5 | High |  |  | Not Started | 0
T195 | 2026-11-05 | W7 | Supporting / QA | Project Control | Archive submitted artefacts and receipts | Submission archive | 0.5 | High |  |  | Not Started | 0
T196 | 2026-11-05 | W7 | Supporting / QA | Project Control | Submit PPRS handout | Submission receipt: handout | 0.5 | High |  | PPRS submitted | Not Started | 0
T197 | 2026-11-05 | W7 | Supporting / QA | Project Control | Submit recorded PPRS video | Submission receipt: video | 0.5 | High |  | PPRS submitted | Not Started | 0
T198 | 2026-11-05 | W7 | Supporting / QA | Project Control | Verify submission portal/access before uploading | Submission access check | 0.5 | High |  |  | Not Started | 0
T199 | 2026-11-05 | W7 | Supporting / QA | Project Control | Verify uploaded files are readable after submission | Post-upload verification | 0.5 | High |  |  | Not Started | 0
T200 | 2026-11-06 | Post-PPRS | 6. Live Presentation | Live Presentation | Add backup slides for datasets, gaps, baselines, ablations and PoC | Backup slides | 1 | High |  |  | Not Started | 0
T201 | 2026-11-06 | Post-PPRS | 6. Live Presentation | Live Presentation | Convert recorded-video slides into live-presentation slides | Live slide deck v0.8 | 1 | High |  |  | Not Started | 0
T202 | 2026-11-06 | Post-PPRS | 6. Live Presentation | Live Presentation | Prepare answers to 10 likely examiner questions | Q&A bank 1 | 1 | High |  |  | Not Started | 0
T203 | 2026-11-07 | Post-PPRS | 6. Live Presentation | Live Presentation | Prepare answers to dataset and feasibility questions | Q&A bank 2 | 1 | High |  |  | Not Started | 0
T204 | 2026-11-07 | Post-PPRS | 6. Live Presentation | Live Presentation | Revise slides after rehearsal defects | Live slide deck v0.9 | 1 | High |  |  | Not Started | 0
T205 | 2026-11-07 | Post-PPRS | 6. Live Presentation | Live Presentation | Run first timed live presentation rehearsal | Rehearsal 1 | 1 | High |  |  | Not Started | 0
T206 | 2026-11-07 | Post-PPRS | 6. Live Presentation | Live Presentation | Run mock Q&A focused on novelty and contribution | Mock viva 1 | 1 | High |  |  | Not Started | 0
T207 | 2026-11-08 | Post-PPRS | 6. Live Presentation | Live Presentation | Finalise live slide deck | Live slide deck v1.0 | 1 | High |  |  | Not Started | 0
T208 | 2026-11-08 | Post-PPRS | 6. Live Presentation | Live Presentation | Prepare 30-second novelty statement | 30-second novelty statement | 0.5 | High |  |  | Not Started | 0
T209 | 2026-11-08 | Post-PPRS | 6. Live Presentation | Live Presentation | Prepare 60-second research summary | 60-second summary | 0.5 | High |  |  | Not Started | 0
T210 | 2026-11-08 | Post-PPRS | 6. Live Presentation | Live Presentation | Prepare fallback plan for PoC/demo failure | Demo fallback plan | 0.5 | High |  |  | Not Started | 0
T211 | 2026-11-08 | Post-PPRS | 6. Live Presentation | Live Presentation | Run full mock live presentation with PoC demonstration | Rehearsal 2 | 1.5 | High |  |  | Not Started | 0
T212 | 2026-11-08 | Post-PPRS | 6. Live Presentation | Live Presentation | Run hostile/critical mock viva on novelty, baselines and limitations | Mock viva 2 | 1.5 | High |  |  | Not Started | 0

## Weekly Plan
Weekly PPRS Plan — Parallel Workstreams
Period | Date Range | Capacity Hours | Planned Hours | LR Focus | Requirement Focus | Handout Focus | PoC Focus | Video / Live Focus | Completion Gate
Start | 20 Sep | 8 | 8 | Audit current LR; flag unsupported claims | Identify requirement sources | Create handout structure; freeze core direction | Confirm dataset risks and repo setup | — | Main gap, sub-gaps and technical contribution provisionally fixed
Week 1 | 21–27 Sep | 27 | 27 | Add missing recent papers; thematic synthesis | Elicit and prioritise functional/non-functional requirements | Draft problem, gap, aim/RQs/objectives | Data ingestion; returns, volatility, liquidity features | — | LR and dataset foundation substantially complete
Week 2 | 28 Sep–4 Oct | 27 | 27 | Challenge novelty; close LR matrix gaps | Freeze Requirements v1.0 and traceability | Write LR themes and dataset strategy | Technical/liquidity/volatility agents; PDF ingestion | — | Methodology, baselines, pipeline and data schema defined
Week 3 | 5–11 Oct | 27 | 27 | Final evidence for main gap + sub-gaps | Requirements continue through verification | Integrated front-half handout draft | Fundamental agent; static orchestration; adaptive rule v0.1 | — | Core scope frozen; static vs adaptive PoC runs
Week 4 | 12–18 Oct | 27 | 27 | No scope expansion; only evidence corrections | Verify requirements against PoC | Methodology, requirements, architecture, pipeline | Adaptive orchestrator; friction evaluation; ablations | — | PoC demonstrates actual proposed contribution; no new scope
Week 5 | 19–25 Oct | 27 | 27 | Citation/gap verification only | Freeze traceability and acceptance criteria | Complete 15-page handout v1.0 | Freeze reproducible PoC evidence | Start video outline | Complete handout v1.0; quality gate ≥4.5/5
Week 6 | 26 Oct–1 Nov | 27 | 27 | No new LR except critical correction | Final verification only | Finalise and proofread handout | Package reproducible PoC evidence | Build slides, script, record final candidate video | All substantive work finished by 1 Nov
Final | 2–5 Nov | 12 | 12 | No new reading | No new elicitation | Final QA and submission | Link/evidence verification only | Freeze and submit recorded video | PPRS handout + video submitted by 5 Nov
Post-PPRS | 6–8 Nov | 20 capacity | 12.5 planned | Use only for viva evidence | — | Convert handout evidence into live deck | Prepare PoC demo fallback | Live rehearsals + mock viva | Live presentation ready immediately after deadline

## Deliverables & Gates
PPRS Deliverables, Definitions of Done, and Quality Gates
Deliverable | Target Date | Definition of Done | Key Evidence | Must Reach Quality | Current Status | Quality /5 | Action if <4.5
1. Literature Review | 25 Oct 2026 | All critical papers read; recent 2025–2026 CSE and global SOTA covered; thematic synthesis written; gap claims supported; remaining absolute claims removed | Literature Survey Matrix + thematic synthesis | ≥4.5/5 | Not Started |  | Read missing papers; improve synthesis; re-check novelty
2. Requirement Elicitation | 22 Oct 2026 | Functional/non-functional/data/evaluation requirements elicited, prioritised, acceptance criteria defined, and traced to RQs/PoC | Requirements specification + traceability matrix | ≥4.5/5 | Not Started |  | Complete missing requirements and traceability
3. PPRS Handout | 4 Nov 2026 | Complete 15-page handout containing introduction/problem background, LR, gap, aim/RQs/objectives, methodology, datasets, requirements, architecture, pipeline, PoC/evaluation and references | Submission-ready handout | ≥4.5/5 | Not Started |  | Revise all weak sections before submission
4. Proof of Concept | 22 Oct 2026 | Data ingestion works; specialist agents produce outputs; static baseline works; adaptive orchestrator works; at least preliminary comparison/ablation evidence exists; reproducible run available | PoC repository + evidence pack | ≥4.5/5 | Not Started |  | Fix feasibility, integration, reproducibility or evidence weakness
5. Recorded PPRS Video | 4 Nov 2026 | Slides and script aligned with handout; research contribution, methodology and PoC explained clearly; timing compliant; final file tested | Final recorded video | ≥4.5/5 | Not Started |  | Re-record after resolving clarity/timing/evidence problems
6. Live Presentation | Immediately after 5 Nov | Live deck, backup slides, PoC demo fallback, novelty statement and examiner Q&A prepared; minimum two rehearsals completed | Live slide deck + Q&A bank + rehearsal log | ≥4.5/5 | Not Started |  | Continue rehearsal and close weak Q&A areas

## Dashboard
PPRS Progress Dashboard
Metric | Value |  | Major Deliverable | Planned Hours | Tasks | Progress %
Deadline | 5 Nov 2026 |  | 1. Literature Review | 25 | 24 | 0
Total atomic tasks | 212 |  | 2. Requirement Elicitation | 13 | 19 | 0
Pre-deadline planned hours | 181 |  | 3. PPRS Handout | 67.5 | 75 | 0
Available pre-deadline hours | 182 |  | 4. Proof of Concept | 37.25 | 40 | 0
Post-deadline live-prep hours | 12.5 |  | 5. Recorded Video | 18.25 | 18 | 0
Completed tasks | 0 |  | 6. Live Presentation | 13 | 14 | 0
In-progress tasks | 0 |  | Supporting / QA | 19.5 | 22 | 0
Blocked tasks | 0
Control Rule: LR + Requirement Elicitation + Handout + PoC must progress simultaneously. No new technical scope after 18 October. Complete handout v1.0 by 24–25 October. All substantive work finished by 1 November.
Workstream | Planned Hours | Share %
Dataset | 1 | 0.5168
Literature Review | 25 | 12.9199
Live Presentation | 13 | 6.7183
Methodology | 11.25 | 5.814
PPRS Handout | 52.25 | 27.0026
PPRS Video | 18.25 | 9.4315
PoC | 36.25 | 18.7339
Project Control | 19.5 | 10.0775
Requirement Elicitation | 13 | 6.7183
Research Design | 4 | 2.0672

## How to Use
How to Use This Tracker
Rule | Instruction
1 | Treat every row in Atomic Task Tracker as an atomic task. Do not mark it complete unless the Evidence / Deliverable exists.
2 | Update Status as Not Started / In Progress / Completed / Blocked.
3 | Enter the actual completion date and evidence/link when a task is completed.
4 | Rate completed work out of 5. Any completed item below 4.5 requires rework.
5 | LR, Requirement Elicitation, Handout and PoC are parallel workstreams; do not finish one and postpone the others.
6 | Do not expand the technical scope after 18 October.
7 | Handout Version 1.0 must exist by 24–25 October; do not wait until November to start writing.
8 | Recorded video must be complete before the 5 November deadline.
9 | Live-presentation preparation begins immediately after the deadline using the submitted research, not by introducing new research.
10 | If a critical dataset or PoC dependency is blocked, mark the task Blocked and record the exact reason and mitigation in Remarks.